## L01560-2024 (hidden)
[7 empty] | 1859103.3 | 1726229.21 | 132874.09 | 7.147% | 2290018.48 | 2122264.16 | 167754.32 | 7.325% | 3186014.71 | 2589779.16 | 596235.55 | 18.71% | 3492524.08 | 2598422.11 | 894101.97 | 25.6% | 10827660.57 | 9036694.64 | 1790965.93 | 16.54%
Legal contract number | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | Plan GP % | Sum of 2024-1Q revenue | Sum of 2024-1Q cost | Sum of 2024-1Q GP | 2024-1Q GP% | Sum of 2024-2Q revenue | Sum of 2024-2Q cost | Sum of 2024-2Q GP | 2024-2Q GP% | Sum of 2024-3Q revenue | Sum of 2024-3Q cost | Sum of 2024-3Q GP | 2024-3Q GP% | Sum of 2024-4Q revenue | Sum of 2024-4Q cost | Sum of 2024-4Q GP | 2024-4Q GP% | Sum of 2024 full year revenue | Sum of 2024 full year cost | 2024 full year GP | 2024 full year GP%
L01560 | UKAGUGV | L01560/NGC-200245 IST - BA for PRI# L01560_NGC-200245_IST - BA for PRI_UKAGUGV | Closed | 2020-06-29 | 2020-12-31 | 25.98% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
L01560 | UKAHAGI | L01560/NGC-210145 - Shipping data and AI squad# L01560_NGC 210145_ Shipping data and AI squad | Closed | 2021-03-17 | 2021-12-31 | 0% | 0 | -1157.2 | 1157.2 | #DIV/0! | 0 | 40.82 | -40.82 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | -1116.38 | 1116.38 | #DIV/0!
L01560 | UKAHHDL | L01560/NGC-210569-3/T&S Australia NAI CR Q3/0063h00000JbJ7eAAF # | Closed | 2021-11-29 | 2024-04-30 | 28.93% | 270067.56 | 163719.5 | 106348.06 | 39.38% | 0 | 107328 | -107328 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 270067.56 | 271047.5 | -979.94 | -0.3628%
L01560 | UKAHMCA | L01560 - NGC-220023-1 - T&S Rubix Q4 / 0063h00000LKQ55AAH # | Closed | 2022-09-15 | 2023-12-31 | 31.35% | 5759.31 | -579.24 | 6338.55 | 110.1% | 0 | -207.56 | 207.56 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 5759.31 | -786.8 | 6546.11 | 113.7%
L01560 | UKAHMUX | L01560 - NGC-220377-3 - T&S EDF Trinity CR Q4 / 0063h00000K3PWnAAN # | Closed | 2022-10-23 | 2023-12-31 | 30.51% | 2170.22 | 2235.7 | -65.48 | -3.017% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 2170.22 | 2235.7 | -65.48 | -3.017%
L01560 | UKAHNIS | L01560 / NGC-220425 - 0063h00000IQGHDAA5 - T&S Pinnacle and Pre Pay | Closed | 2022-12-05 | 2023-12-22 | 30.44% | 0 | 2352.96 | -2352.96 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 2352.96 | -2352.96 | #DIV/0!
L01560 | UKAHNKX | L01560 / NGC-220467 - 0063h00000HVkE7AAL - T&S Brazil - Diesel | Closed | 2022-11-28 | 2024-01-17 | 27.59% | 10543.23 | 9924.98 | 618.25 | 5.864% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 10543.23 | 9924.98 | 618.25 | 5.864%
L01560 | UKAHNLF | L01560/NGC- 220446/T&S Brazil - Rio/0063h00000JEffdAAD # | Closed | 2022-11-28 | 2024-01-17 | 27.59% | 10543.23 | 10833.01 | -289.78 | -2.748% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 10543.23 | 10833.01 | -289.78 | -2.748%
L01560 | UKAHNPM | -L01560/NGC-220459/T&S DevOps Roles 2023/0063h00000K18SqAAJ # | Closed | 2023-01-01 | 2023-12-31 | 26.43% | 1849.31 | 1164.89 | 684.42 | 37.01% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 1849.31 | 1164.89 | 684.42 | 37.01%
L01560 | UKAHOAR | L01560/NGC-220512 - T&S Delivery Programme Management / 0063h00000K1qgQAAR # | Closed | 2022-12-12 | 2023-12-31 | 20.69% | 0 | 5142.56 | -5142.56 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 5142.56 | -5142.56 | #DIV/0!
L01560 | UKAHOGK | L01560 - NGC-220549 - T&S EVC Spain / 0063h00000IPQYBAA5 # | Closed | 2023-01-16 | 2023-02-24 | 0% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0!
L01560 | UKAHOPI | L01560 - NGC-220549 - T&S EVC Spain / 0063h00000IPQYBAA5 # | Closed | 2023-01-16 | 2024-09-30 | 30.99% | 0 | 147344.34 | -147344.34 | #DIV/0! | 0 | -18794 | 18794 | #DIV/0! | 0 | 60109.42 | -60109.42 | #DIV/0! | 0 | 803.86 | -803.86 | #DIV/0! | 0 | 189463.62 | -189463.62 | #DIV/0!
L01560 | UKAHPGD | L01560/NGC-230147/ GM Euro Cons Unit/0063h00000K3PX2AAN # | Closed | 2023-03-31 | 2024-04-30 | 29.89% | 0 | 32727.63 | -32727.63 | #DIV/0! | 0 | 3073.57 | -3073.57 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 35801.2 | -35801.2 | #DIV/0!
L01560 | UKAHPGR | L01560 / NGC-230096 - T&S Cost Management # | Closed | 2023-03-15 | 2024-06-30 | 28.84% | -85.96 | 382.47 | -468.43 | 544.9% | 0 | 191.89 | -191.89 | #DIV/0! | 0 | 132.71 | -132.71 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | -85.96 | 707.07 | -793.03 | 922.6%
L01560 | UKAHPTZ | L01560 - NGC-230095-2 - GPT Japan NAI / 0063h00000LLVmMAAX # | Active | 2023-05-01 | 2024-12-30 | 24.42% | 136356.99 | 107292.34 | 29064.65 | 21.32% | 62199.75 | 192188.18 | -129988.43 | -209% | 22027.97 | 30034.94 | -8006.97 | -36.35% | 33041.96 | 34660.19 | -1618.23 | -4.898% | 253626.67 | 364175.65 | -110548.98 | -43.59%
L01560 | UKAHPWP | L01560/NGC-230236-0063h00000LAtM0AAL-T&S Enhancements 2H23 | Closed | 2023-05-01 | 2023-12-31 | 29.74% | 3393.09 | 15484.19 | -12091.1 | -356.3% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 3393.09 | 15484.19 | -12091.1 | -356.3%
L01560 | UKAHRHQ | L01560 - NGC-230336-3 - TF&T Supply Chain Finance CR2 / 006Ka00000NTjEhIAL # | Active | 2023-08-13 | 2025-06-27 | 19.83% | 194469.77 | 133033.59 | 61436.18 | 31.59% | 299892.5 | 271478.59 | 28413.91 | 9.475% | 177783.04 | 296184.61 | -118401.57 | -66.6% | -27363.74 | 29012.74 | -56376.48 | 206% | 644781.57 | 729709.53 | -84927.96 | -13.17%
L01560 | UKAHSAY | L01560 - NGC- 230339-3 - GPT South Africa Interim Supply Model - CR3 / 0063h00000MCyDTAA1 # | Closed | 2023-09-18 | 2024-07-31 | 27.14% | 125391.52 | 212866.56 | -87475.04 | -69.76% | 128812.1 | 124688.59 | 4123.51 | 3.201% | 59568.2 | 33246.59 | 26321.61 | 44.19% | 0 | 0 | 0 | #DIV/0! | 313771.82 | 370801.74 | -57029.92 | -18.18%
L01560 | UKAHSWZ | L01560 - NGC-230148-1 - RPT&I Cost Management Marine CR / 0063h00000MCY3rAAH # | Active | 2023-11-15 | 2025-07-31 | 19.59% | 159678.83 | 134308.11 | 25370.72 | 15.89% | 150791.46 | 125008.54 | 25782.92 | 17.1% | 103340.66 | 79808.37 | 23532.29 | 22.77% | 44010.48 | 49812.45 | -5801.97 | -13.18% | 457821.43 | 388937.47 | 68883.96 | 15.05%
L01560 | UKAHTAF | L01560 - NGC-230261 - TSD RPT Brazil / 0063h00000LAuOHAA1 # | Closed | 2024-01-01 | 2024-10-31 | 24.24% | 134069 | 102179.66 | 31889.34 | 23.79% | 170734.84 | 147243.2 | 23491.64 | 13.76% | 313529.91 | 251224.93 | 62304.98 | 19.87% | 197745.85 | 116578.14 | 81167.71 | 41.05% | 816079.6 | 617225.93 | 198853.67 | 24.37%
L01560 | UKAHTAJ | L01560 - NGC-230346 - TSD Blueprint FCC / 0063h00000LJZSTAA5 # | Active | 2023-11-13 | 2024-12-30 | 22.41% | 139713.11 | 120981.46 | 18731.65 | 13.41% | 198198.01 | 162929.81 | 35268.2 | 17.79% | 308248.9 | 215982.63 | 92266.27 | 29.93% | 484565.05 | 383565.68 | 100999.37 | 20.84% | 1130725.07 | 883459.58 | 247265.49 | 21.87%
L01560 | UKAHTAL | L01560/NGC-230098/TSD GPTA Brazil/0063h00000K1IoUAAV # | Closed | 2024-01-01 | 2024-10-31 | 25.7% | 107233 | 85092.01 | 22140.99 | 20.65% | 138693.17 | 111041.21 | 27651.96 | 19.94% | 267938.95 | 183431.72 | 84507.23 | 31.54% | 158664.96 | 123128.65 | 35536.31 | 22.4% | 672530.08 | 502693.59 | 169836.49 | 25.25%
L01560 | UKAHTAP | L01560 - NGC-230437-2 - TF&T KPI Dashboard CR2 / 006Ka00000NTjEOIA1 # | Active | 2023-11-20 | 2024-12-31 | 22.72% | 155597 | 124226.46 | 31370.54 | 20.16% | 206872.14 | 163923.47 | 42948.67 | 20.76% | 206672.6 | 143613.01 | 63059.59 | 30.51% | 245910.08 | 187391.79 | 58518.29 | 23.8% | 815051.82 | 619154.73 | 195897.09 | 24.03%
L01560 | UKAHTDZ | L01560/NGC-230205/ TSD Dashboard Analytics/0063h00000K3PrOAAV | Closed | 2023-12-11 | 2024-06-30 | 24.97% | 100427.34 | 79513.81 | 20913.53 | 20.82% | 50019 | 38808.84 | 11210.16 | 22.41% | 0 | 50.06 | -50.06 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 150446.34 | 118372.71 | 32073.63 | 21.32%
L01560 | UKAHUBZ | L01560 /NGC-220023-3/L01560 - T&S Rubix Data/0063h00000MBoWMAA1 # | Active | 2024-01-01 | 2024-12-20 | 26.36% | 44867.67 | 35155.5 | 9712.17 | 21.65% | 49028.85 | 34098.99 | 14929.86 | 30.45% | 39664.83 | 35463.13 | 4201.7 | 10.59% | 50032.86 | 30266.58 | 19766.28 | 39.51% | 183594.21 | 134984.2 | 48610.01 | 26.48%
L01560 | UKAHUCV | L01563 -NGC-230403-2- TF&T - HARP 2025 - 0063h00000MCEawAAH # | Active | 2023-11-27 | 2025-12-31 | 18.93% | 171686.22 | 137741.09 | 33945.13 | 19.77% | 171792.47 | 135739.7 | 36052.77 | 20.99% | 244600.97 | 177225.53 | 67375.44 | 27.55% | 145471.81 | 159865.95 | -14394.14 | -9.895% | 733551.47 | 610572.27 | 122979.2 | 16.76%
L01560 | UKAHUDM | L01560 - NGC-230188 -1- RPT&I Project STAR Phase 2/ 0063h00000MCY3JAAX # | Active | 2024-02-01 | 2025-01-17 | 22.14% | 39126 | 45850.9 | -6724.9 | -17.19% | 195435.09 | 162274.19 | 33160.9 | 16.97% | 332244.5 | 233228.58 | 99015.92 | 29.8% | 306939.62 | 262210.88 | 44728.74 | 14.57% | 873745.21 | 703564.55 | 170180.66 | 19.48%
L01560 | UKAHUKP | L01560 - NGC-240030-1-GPT Hyperion - Power and Brazil Wholesalel / 0063h00000MClvMAAT # | Active | 2024-03-01 | 2026-06-30 | 21.26% | 7755 | 5401.67 | 2353.33 | 30.35% | 199039.18 | 139319.23 | 59719.95 | 30% | 99268.55 | 106202.1 | -6933.55 | -6.985% | 6092.12 | 12496.39 | -6404.27 | -105.1% | 312154.85 | 263419.39 | 48735.46 | 15.61%
L01560 | UKAHUPP | L01560 /NGC-230187/ TF&T DevOps Roles/0063h00000K3XIYAA3 # | Active | 2024-01-01 | 2024-12-31 | 28.87% | 38491.86 | 13010.26 | 25481.6 | 66.2% | 31093.05 | 25409.96 | 5683.09 | 18.28% | 9836.72 | 21067.02 | -11230.3 | -114.2% | 61217.8 | 38702.98 | 22514.82 | 36.78% | 140639.43 | 98190.22 | 42449.21 | 30.18%
L01560 | UKAHURV | L01560 - NGC-240033 - 1- TFT Ghana CR (Credit) / 006Ka00000NTo9uIAD # | Closed | 2024-03-15 | 2024-10-11 | 27.96% | 0 | 0 | 0 | #DIV/0! | 104709.58 | 80860.67 | 23848.91 | 22.78% | 130878.33 | 104092.01 | 26786.32 | 20.47% | 54829.13 | 25714.47 | 29114.66 | 53.1% | 290417.04 | 210667.15 | 79749.89 | 27.46%
L01560 | UKAHVRH | L01560 - NGC-240057-3 -ITK Silverstone - Define 1 / 006Ka00000NT1gRIAT # | Active | 2024-05-13 | 2025-02-14 | 12.97% | 0 | 0 | 0 | #DIV/0! | 123765.53 | 108017.77 | 15747.76 | 12.72% | 378509.34 | 279119.76 | 99389.58 | 26.26% | 926988.23 | 590811.52 | 336176.71 | 36.27% | 1429263.1 | 977949.05 | 451314.05 | 31.58%
L01560 | UKAHVZJ | L01560/ NGC-240061/ TFT Recharges/006Ka00000NOsNIIA1 # | Active | 2024-06-10 | 2024-12-20 | 18.99% | 0 | 0 | 0 | #DIV/0! | 8941.76 | 7600.5 | 1341.26 | 15% | 112071.06 | 91236.67 | 20834.39 | 18.59% | 143837.77 | 126675.76 | 17162.01 | 11.93% | 264850.59 | 225512.93 | 39337.66 | 14.85%
L01560 | UKAHWPI | L01560/NGC-240077/GPT GETEC Holding Company/ 006Ka00000NT1gBIAT# | Active | 2024-07-15 | 2025-02-28 | 21.82% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 63624.25 | 14974.81 | 48649.44 | 76.46% | 78594.63 | 2046.99 | 76547.64 | 97.4% | 142218.88 | 17021.8 | 125197.08 | 88.03%
L01560 | UKAHWRU | L01560 - TFT - TSD CSO | Active | 2024-07-22 | 2024-12-27 | 20.1% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 26324.46 | 15876.39 | 10448.07 | 39.69% | 32174.34 | 30466.18 | 1708.16 | 5.309% | 58498.8 | 46342.57 | 12156.23 | 20.78%
L01560 | UKAHWZI | L01560 - NGC-240040 - RPT&I Australia Supply OM / 006Ka00000NVx1nIAD # | Active | 2024-08-12 | 2024-12-27 | 20.87% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 156520.7 | 93563.52 | 62957.18 | 40.22% | 0 | 565.59 | -565.59 | #DIV/0! | 156520.7 | 94129.11 | 62391.59 | 39.86%
L01560 | UKAHWZJ | L01560/NGC-240089/TF&T - Finance Process Automation/006Ka00000NTjEmIAL # | Active | 2024-08-12 | 2024-12-31 | -2.381% | 0 | 0 |  |  | 0 | 0 |  |  | 133360.77 | 118737.48 | 14623.29 | 10.97% | 172584.5 | 265871.58 | -93287.08 | -54.05% | 305945.27 | 384609.06 | -78663.79 | -25.71%
L01560 | UKAHXAK | L01560 - NGC-240097-Op Model Automation/006Ka00000NUqUaIAL # | Closed | 2024-08-19 | 2024-10-18 | 14.6% | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 5173.17 | -5173.17 | #DIV/0! | 11600.47 | 4373.57 | 7226.9 | 62.3% | 11600.47 | 9546.74 | 2053.73 | 17.7%
L01560 | UKAHXNG | L01560/NGC-240102/RPT&I Nigeria /006Ka00000NUql7IAD# | Active | 2024-10-01 | 2025-07-11 | 11.99% | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 194150.93 | 5544.44 | 188606.49 | 97.14% | 194150.93 | 5544.44 | 188606.49 | 97.14%
L01560 | UKAHXOM | N/A | Pre-contract no bill | 2024-09-30 | 2024-11-24 | 0% | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 21172.83 | -21172.83 | #DIV/0! | 0 | 21172.83 | -21172.83 | #DIV/0!
L01560 | UKAHYAH | L01560 NGC-240128/ GPT LNG Transformation/006Ka00000NW6qLIAT# | Active | 2024-11-01 | 2025-07-31 | 22.6% | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 66050.56 | 59647.76 | 6402.8 | 9.694% | 66050.56 | 59647.76 | 6402.8 | 9.694%
L01560 | UKAHYHH | L01560/ NGC-240127/RPT - Brazil Crude/006Ka00000NW6quIAD# | Active | 2024-11-25 | 2025-06-30 | 4.996% | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 31180 | 37035.14 | -5855.14 | -18.78% | 31180 | 37035.14 | -5855.14 | -18.78%
L01560 | UKAHYMV | L01560/NGC-230102/TF&T Integrated Value Select/0063h00000K3PbJAAV# | Active | 2024-12-05 | 2025-02-28 | 22.44% | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 74204.67 | 0 | 74204.67 | 100% | 74204.67 | 0 | 74204.67 | 100%
Grand Total | [6 empty] | 1859103.3 | 1726229.21 | 132874.09 | 7.147% | 2290018.48 | 2122264.16 | 167754.32 | 7.325% | 3186014.71 | 2589779.16 | 596235.55 | 18.71% | 3492524.08 | 2598422.11 | 894101.97 | 25.6% | 10827660.57 | 9036694.64 | 1790965.93 | 16.54%
[22 empty] | With AM Cost | 10827660.57 | 9448974.49 | 1378686.08 | 12.73%

## STS-2025 (hidden)
|  | L01560 + L01565 Total - |  |  |  |  | 7385884.106 | 5962008.908 | 1423875.198 | 19.28% | 9109312.5985 | 7879316.996 | 1229995.6025 | 13.5% | 12795550.0955 | 10560170.4135 | 2235379.682 | 17.47% | 13997975.7705 | 11398688.5145 | 2599287.256 | 18.57%
[7 empty] | 5376396.6345 | 4600165.733 | 776230.9015 | 14.44% | 6946597.862 | 6396821.6815 | 549776.1805 | 7.914% | 9866055.6445 | 8351775.0225 | 1514280.622 | 15.35% | 11079087.8455 | 9258157.9205 | 1820929.925 | 16.44% | Rev Target : 13.50 M
[7 empty] | 3468642.99 | 2967848.86 | 500794.13 | 14.44% | 4481676.04 | 4126981.73 | 354694.31 | 7.914% | 6365197.19 | 5388241.95 | 976955.24 | 15.35% | 7147798.61 | 5973005.11 | 1174793.5 | 16.44% | GP Target : 16 above
Legal contract number | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | Plan GP % | 2025-1Q revenue | 2025-1Q cost | 2025-1Q GP | 2025-1Q GP% | 2025-2Q revenue | 2025-2Q cost | 2025-2Q GP | 2025-2Q GP% | 2025-3Q revenue | 2025-3Q cost | 2025-3Q GP | 2025-3Q GP% | 2025-4Q revenue | 2025-4Q cost | 2025-4Q GP | 2025-4Q GP% | Type | Remarks | Variance reason
L01560 | UKAGUGX | AM | Active | 2020-06-29 | 2026-12-31 | 0% | 0 | 155544.35 | -155544.35 | #DIV/0! | 0 | 121343.78 | -121343.78 | #DIV/0! | 0 | 353765.44 | -353765.44 | #DIV/0! | 0 | 235551.05 | -235551.05 | #DIV/0! | NA
L01560 | UKAHPTZ | L01560 - NGC-230095-2 - GPT Japan NAI / 0063h00000LLVmMAAX # | Closed | 2023-05-01 | 2024-12-30 | 24.42% | 0 | 58.3 | -58.3 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0! | Non POC
L01560 | UKAHRHQ | L01560 - NGC-230336-3 - TF&T Supply Chain Finance CR2 / 006Ka00000NTjEhIAL # | Closed | 2023-08-13 | 2025-06-27 | 19.83% | 137674.1 | 95052.79 | 42621.31 | 30.96% | 301290.88 | 261475.19 | 39815.69 | 13.22% | -446.96 | -4640.44 | 4193.48 | -938.2% |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHSWZ | L01560 - NGC-230148-1 - RPT&I Cost Management Marine CR / 0063h00000MCY3rAAH # | Closed | 2023-11-15 | 2025-07-31 | 19.59% | 147491.61 | 98302.31 | 49189.3 | 33.35% | 128822.37 | 117340.5 | 11481.87 | 8.913% | 271788.97 | 55887.45 | 215901.52 | 79.44% | -291.33 | 665.52 | -956.85 | 328.4% | MPOC
L01560 | UKAHTAJ | L01560 - NGC-230346 - TSD Blueprint FCC / 0063h00000LJZSTAA5 # | Closed | 2023-11-13 | 2024-12-30 | 22.41% | -2735.5 | 2116.05 | -4851.55 | 177.4% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHTAP | L01560 - NGC-230437-2 - TF&T KPI Dashboard CR2 / 006Ka00000NTjEOIA1 # | Closed | 2023-11-20 | 2024-12-31 | 22.72% | 1810.65 | 2356.16 | -545.51 | -30.13% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHUBZ | L01560 /NGC-220023-3/L01560 - T&S Rubix Data/0063h00000MBoWMAA1 # | Closed | 2024-01-01 | 2024-12-20 | 26.36% | -1004 | -1173.33 | 169.33 | -16.87% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | Non POC
L01560 | UKAHUCV | L01563 -NGC-230403-2- TF&T - HARP 2025 - 0063h00000MCEawAAH # | Active | 2023-11-27 | 2025-12-31 | 18.93% | 283590.94 | 226219.85 | 57371.09 | 20.23% | 213312.55 | 202168.51 | 11144.04 | 5.224% | 243971.06 | 209252.32 | 34718.74 | 14.23% | 418815.72 | 324213.01 | 94602.71 | 22.59% | MPOC
L01560 | UKAHUDM | L01560 - NGC-230188 -1- RPT&I Project STAR Phase 2/ 0063h00000MCY3JAAX # | Closed | 2024-02-01 | 2025-01-17 | 22.14% | 164805.76 | 110139.93 | 54665.83 | 33.17% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHUKP | L01560 - NGC-240030-2-GPT Hyperion - Power and Brazil Wholesale CR- 006gR000000LljtQAC # | Active | 2024-03-01 | 2026-12-31 | 25.16% | 26745.4 | 14244.96 | 12500.44 | 46.74% | 454814.69 | 400449.32 | 54365.37 | 11.95% | 238288.17 | 161486.76 | 76801.41 | 32.23% | 0 | 2179.8 | -2179.8 | #DIV/0! | MPOC | Project is paused, no plan yet.
L01560 | UKAHUPP | L01560 /NGC-230187/ TF&T DevOps Roles/0063h00000K3XIYAA3 # | Closed | 2024-01-01 | 2024-12-31 | 28.87% | 2006.43 | 951.58 | 1054.85 | 52.57% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHVRH | L01560 - NGC-240057-4 -ITK Silverstone - Define 2 / 006Ka00000NWCzsIAH # | Active | 2024-05-13 | 2025-10-31 | 12.97% | 1049317.05 | 933989.14 | 115327.91 | 10.99% | 1738292.92 | 1681514.96 | 56777.96 | 3.266% | 1783860.15 | 1676087.13 | 107773.02 | 6.042% | 586551.08 | 590176.59 | -3625.51 | -0.6181% | MPOC
L01560 | UKAHVZJ | L01560/ NGC-240061/ TFT Recharges/006Ka00000NOsNIIA1 # | Closed | 2024-06-10 | 2024-12-20 | 18.99% | 14856.67 | 0 | 14856.67 | 100% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHWPI | L01560/NGC-240077/GPT GETEC Holding Company/ 006Ka00000NT1gBIAT# | Closed | 2024-07-15 | 2025-02-28 | 21.82% | 44911.23 | 134817.09 | -89905.86 | -200.2% | 0 | 0.18 | -0.18 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | Non POC
L01560 | UKAHWZJ | L01560/NGC-240089/TF&T - Finance Process Automation/006Ka00000NTjEmIAL # | Closed | 2024-08-12 | 2024-12-31 | -2.381% | 86292.26 | 319.05 | 85973.21 | 99.63% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | Non POC
L01560 | UKAHXNG | L01560/NGC-240102/RPT&I Nigeria /006Ka00000NUql7IAD# | Active | 2024-10-01 | 2025-12-31 | 11.99% | 90204.39 | 124534.92 | -34330.53 | -38.06% | 58832.13 | 45294.3 | 13537.83 | 23.01% | 58832 | 85483.88 | -26651.88 | -45.3% | 88248.5 | 144194.76 | -55946.26 | -63.4% | Non POC | Project was onhold and zero value extension done till Dec 25, Project re-started from Jul with less cost hence Rev (May, Jun, Jul) pushed to Sep till Dec.
L01560 | UKAHYAH | L01560 NGC-240128/ GPT LNG Transformation/006Ka00000NW6qLIAT# | Active | 2024-11-01 | 2025-11-30 | 22.6% | 58407.17 | 40527.18 | 17879.99 | 30.61% | 65135.44 | 52208.28 | 12927.16 | 19.85% | 221607.36 | 189247.44 | 32359.92 | 14.6% | 89560.61 | 44270.18 | 45290.43 | 50.57% | MPOC | Zero value extension till 30 Nov 25
L01560 | UKAHYHH | L01560/ NGC-240127/RPT - Brazil Crude/006Ka00000NW6quIAD# | Closed | 2024-11-25 | 2025-06-30 | 4.996% | 336120.8 | 305517.84 | 30602.96 | 9.105% | 279534.61 | 276752.66 | 2781.95 | 0.9952% | 0 | -2075.26 | 2075.26 | #DIV/0! |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHYMV | L01560/NGC-230102/TF&T Integrated Value Select/0063h00000K3PbJAAV# | Closed | 2024-12-05 | 2025-03-21 | 22.44% | 118177.82 | 146647.26 | -28469.44 | -24.09% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | System Periodization
L01560 | UKAHYPJ | L01560 - NGC-240158-1 -- TF&T - Finance Process Automation - CR 1 / 006gR0000009fyPQAQ # | Active | 2024-12-02 | 2025-12-31 | 16.41% | 333805.5 | 292832.59 | 40972.91 | 12.27% | 213460.27 | 170393.17 | 43067.1 | 20.18% | 190947.59 | 172754.61 | 18192.98 | 9.528% | 205944.79 | 168876.99 | 37067.8 | 18% | MPOC
L01560 | UKAHYXI | L01560 - NGC-240160-1 -RPT UX Strategy H2 2025 / 006gR000000AdxnQAC # | Active | 2025-01-13 | 2025-12-31 | 14.44% | 182882.61 | 139562 | 43320.61 | 23.69% | 168491.02 | 161296.2 | 7194.82 | 4.27% | 181546.01 | 169133.33 | 12412.68 | 6.837% | 63359.39 | 39421.5 | 23937.89 | 37.78% | MPOC
L01560 | UKAHZKP | L01560 - GPT - Brazil Nfe / 006Ka00000NWK22IAH | Active | 2025-01-01 | 2025-12-05 | 17.18% | 66887.5 | 57368.56 | 9518.94 | 14.23% | 108853.5 | 90579.25 | 18274.25 | 16.79% | 479287.65 | 424065.33 | 55222.32 | 11.52% | 550683.06 | 409269.85 | 141413.21 | 25.68% | MPOC
L01560 | UKAHZKR | L01560 - -NGC-240164-3TF&T - ARC Extension (Constellation & Scout)/006gR000001T7NKQA0# | Active | 2025-01-02 | 2025-12-31 | 18.86% | 185732.07 | 120641.88 | 65090.19 | 35.05% | 156981.23 | 164921.15 | -7939.92 | -5.058% | 217783.2 | 193773.2 | 24010 | 11.02% | 176078.54 | 130348.93 | 45729.61 | 25.97% | MPOC
L01560 | UKAHZQI | L01560/NGC-240161-1/ TF&T - E2E Process Review (Compass)/006gR000000IvXkQAK# | Closed | 2025-01-20 | 2025-09-30 | 15.25% | 124112.73 | 108957.59 | 15155.14 | 12.21% | 174968.15 | 155129.8 | 19838.35 | 11.34% | 180235.38 | 155333.33 | 24902.05 | 13.82% | 17301.17 | 4139.31 | 13161.86 | 76.07% | MPOC
L01560 | UKAHZRH | L01560/NGC-240226/L01560 - GPT SRA SAP Canada/006Ka00000NWiKcIAL# | Closed | 2025-01-01 | 2025-07-31 | 19.33% | 16549.8 | 13865.16 | 2684.64 | 16.22% | 218794.04 | 189478.55 | 29315.49 | 13.4% | 15063.42 | -9601.73 | 24665.15 | 163.7% |  |  | 0 | #DIV/0! | MPOC
L01560 | UKAHZVJ | N/A | Rejected | 2025-02-03 | 2025-03-14 | 0% |  |  | 0 | #DIV/0! |  | -10521.21 | 10521.21 | #DIV/0! |  |  | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01560 | UKAIANF | L01560/NGC-250012/ ST&S Silverstone - ANZ/006Ka00000QVniqIAD# | Active | 2025-04-01 | 2025-11-30 | 22.16% |  |  |  |  | 200092.24 | 164149.89 | 35942.35 | 17.96% | 253818.91 | 208003.47 | 45815.44 | 18.05% | 887462.62 | 690022.04 | 197440.58 | 22.25% | MPOC
L01560 | UKAIBDZ | L01560-NGC-250014-GPTI Euro Cons Unit Migration /006Ka00000QWgUuIAL # | Closed | 2025-05-01 | 2025-08-15 | 25.7% |  |  |  |  | 0 | 4351.03 | -4351.03 | #DIV/0! | 85902.5 | 56900.99 | 29001.51 | 33.76% | 0 | 32.48 | -32.48 | #DIV/0! | Non POC
L01560 | UKAIBWF | L01560/NGC-250019/ST&S Brazil Marine gasoi/006Ka00000QVtCzIAL# | Active | 2025-06-02 | 2026-03-27 | 31.32% |  |  |  |  | 0 | 0 | 0 | #DIV/0! | 203872.5 | 50449.14 | 153423.36 | 75.25% | 203872.5 | 50288.24 | 153584.26 | 75.33% | Non POC
L01560 | UKAIBWY | L01560/NGC-250029/ ST&S BR Tax Reforms/006Ka00000QVtCuIAL# | Active | 2025-06-16 | 2026-02-27 | 16.84% |  |  |  |  | 0 | 7573.32 | -7573.32 | #DIV/0! | 111995.68 | 91083.54 | 20912.14 | 18.67% | 117275.63 | 97370.53 | 19905.1 | 16.97% | MPOC
L01560 | UKAIBZS | L01560 - ST&S Trading Finance Derivatives Activity/006Ka00000QVkVhIAL# | Active | 2025-07-01 | 2026-12-31 | 15.38% | [7 empty] | #DIV/0! | 185777.46 | 169170.4 | 16607.06 | 8.939% | 299145.08 | 253635.43 | 45509.65 | 15.21% | MPOC
L01560 | UKAICDT | L01560 -NGC-250020- ST&S Silverstone - Europe and IDM /006gR000000JYagQAG # | Active | 2025-06-02 | 2026-07-17 | 15.92% | [7 empty] | #DIV/0! | 912113.41 | 822404.11 | 89709.3 | 9.835% | 2139860.83 | 1850278.09 | 289582.74 | 13.53% | MPOC | Zero value extension done till 17th Jul 2026
L01560 | UKAICDX | L01560 -NGC-250025- ST&S PRI Pre Work/006Ka00000NW82rIAD# | Active | 2025-06-16 | 2025-12-31 | 6.851% | [7 empty] | #DIV/0! | 378438.52 | 372396.62 | 6041.9 | 1.597% | 567802.99 | 506918.38 | 60884.61 | 10.72% | MPOC
L01560 | UKAICMC | N/A | Pre-contract no bill | 2025-07-21 | 2025-10-31 | 0% | [12 empty] | 0 | 0 | 0 | #DIV/0!
L01560 | UKAICNK | L01560/NGC-230148-2/ RPT Cost Management Marine CR/006Ka00000QWBagIAH# | Active | 2025-08-01 | 2026-01-31 | 17.43% | [7 empty] | #DIV/0! | 73727.9 | 65077.89 | 8650.01 | 11.73% | 71461.85 | 57695.11 | 13766.74 | 19.26% | MPOC
L01560 | UKAICRW | L01560-NGC-250033 - 1-ST&S Golden Phoenix (CN1 - Data Scientists)-006gR000001VfUZQA0 # | Active | 2025-08-18 | 2025-12-19 | 3.935% | [8 empty] | 76786.31 | 73500.59 | 3285.72 | 4.279% | 284787.48 | 256652.3 | 28135.18 | 9.879% | MPOC
L01560 | UKAICTX | L01560 - NGC-250044-1-Silver Stone - ST&S Risk Insights /006gR000001odtfQAA # | Active | 2025-08-18 | 2026-06-30 | 17.25% | [8 empty] | 0 | 3067.85 | -3067.85 | #DIV/0! | 80111.94 | 65820.73 | 14291.21 | 17.84% | MPOC
L01560 | UKAICZB | N/A | Pre-contract no bill | 2025-09-08 | 2025-10-10 | 0% | [12 empty] | 0 | 0 | 0 | #DIV/0!
L01560 | UKAIDAN | N/A | Rejected | 2025-09-10 | 2025-11-10 | 100% | [12 empty] | 0 | -124.69 | 124.69 | #DIV/0!
L01560 | UKAIDEU | L10560 - NGC-250049-ARC Finance Process Automation-006gR000001Yus2QAC # | Active | 2025-10-01 | 2026-04-30 | 4.567% | [12 empty] | 271517.36 | 262814.21 | 8703.15 | 3.205% | MPOC
L01560 | UKAIDPO | L01560 - NGC-250055-/ST&S GPTI Endur Settlements/006gR0000028XyYQAU# | Active | 2025-10-01 | 2025-12-31 | 18.15% | [12 empty] | 28248.8 | 23845.82 | 4402.98 | 15.59% | MPOC
Grand Total | [6 empty] | 3468642.99 | 3123393.21 | 345249.78 | 9.953% | 4481676.04 | 4255898.83 | 225777.21 | 5.038% | 6365197.19 | 5742007.39 | 623189.8 | 9.791% | 7147798.61 | 6208556.16 | 939242.45 | 13.14%
[7 empty] | 2009487.4715 | 1361843.175 | 647644.2965 | 32.23% | 2162714.7365 | 1482495.3145 | 680219.422 | 31.45% | 2929494.451 | 2208395.391 | 721099.06 | 24.62% | 2918887.925 | 2140530.594 | 778357.331 | 26.67%
[7 empty] | 1296443.53 | 878608.5 | 417835.03 | 32.23% | 1395299.83 | 956448.59 | 438851.24 | 31.45% | 1889996.42 | 1424771.22 | 465225.2 | 24.62% | 1883153.5 | 1380987.48 | 502166.02 | 26.67%
Legal contract number | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | Plan GP % | 2025-1Q revenue | 2025-1Q cost | 2025-1Q GP | 2025-1Q GP% | 2025-2Q revenue | 2025-2Q cost | 2025-2Q GP | 2025-2Q GP% | 2025-3Q revenue | 2025-3Q cost | 2025-3Q GP | 2025-3Q GP% | 2025-4Q revenue | 2025-4Q cost | 2025-4Q GP | 2025-4Q GP% | Type | Remarks | Notes
L01565 | UKAHHSG | PMO | Active | 2022-01-01 | 2026-12-31 | 0% | 0 | 3475.2 | -3475.2 | #DIV/0! | 0 | 96409.97 | -96409.97 | #DIV/0! | 0 | 69603.92 | -69603.92 | #DIV/0! | 0 | 16998.56 | -16998.56 | #DIV/0!
L01565 | UKAHHSH | AM | Active | 2022-01-01 | 2026-12-31 | 0% | 0 | 181084.27 | -181084.27 | #DIV/0! | 0 | 45365.83 | -45365.83 | #DIV/0! | 0 | 80320.69 | -80320.69 | #DIV/0! | 0 | 203390.09 | -203390.09 | #DIV/0!
L01565 | UKAHTKW | L01565 - NGC-230417 -2- Bioverse Neg. Change Note (Rajiv & Umesh) / 0063h00000LW7OdAAL # | Closed | 2024-01-01 | 2024-12-31 | 10.8% | 1793.57 | 389.17 | 1404.4 | 78.3% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHTTS | L01565 - NGC-230041-3 - L01565 - GIPP Polaris 2024 H2 (Renewal)/ 0063h00000LW7TmAAL # | Closed | 2024-01-01 | 2024-12-31 | 5.474% | 7886.33 | 573.83 | 7312.5 | 92.72% | 8188.83 | 0 | 8188.83 | 100% | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHTTU | L01565//NGC-230041-5/ GIPP Polaris 2024 Q3&Q4 (Top-Up)//006Ka00000NXxD3IAL # | Closed | 2024-01-01 | 2024-12-31 | 33.24% | 1024.34 | -12728.46 | 13752.8 | 1343% | 0 | 27830.91 | -27830.91 | #DIV/0! | 0 | 272.52 | -272.52 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHWGR | L01565 - NGC-230420-2 - TSD Cross Portfolio Support Q4 2024 (Renewal) | Closed | 2024-07-01 | 2024-12-31 | -88.63% | 0.01 | 0 | 0.01 | 100% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHWII | L01565 - NGC-230419-3- GIPP Pricing Data 2024 H2 (US Workstream) - Renewal -006Ka00000NY0gwIAD # | Closed | 2024-07-01 | 2024-12-31 | -3.124% | 5561.79 | 778.34 | 4783.45 | 86.01% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHWIK | L01565 -NGC-230416-2- GIPP Pricing Data 2024 H2 (Europe Workstream)-Renewal/006Ka00000NY0h1IAD# | Closed | 2024-07-01 | 2024-12-31 | 31.13% | 3877.15 | 3037.37 | 839.78 | 21.66% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHWNK | L01565 - NGC-230041-5- GIPP Polaris 2024 Q3&Q4 (Top-Up)/006Ka00000NXxD3IAL # | Closed | 2024-07-08 | 2024-12-31 | 34.04% | 2878.38 | 746.5 | 2131.88 | 74.07% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHXAL | L01565 - NGC-240096-2 - GIPP PRISMA Nov-Dec (Expansion) / 006Ka00000NYUhMIAX # | Closed | 2024-08-19 | 2024-12-31 | 40.44% | -75723.16 | 3519.9 | -79243.06 | 104.6% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHXKW | L01565 - NGC-240096-1-GIPP PRISMA H2 2024 - DE CN-006Ka00000NYSQjIAP# | Closed | 2024-09-16 | 2024-12-31 | 35.84% | 468.27 | 0 | 468.27 | 100% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHXOY | L01565/ NGC-240096/GIPP Polaris Analytics H2 2024 (PRISMA)/0063h00000LoLA6AAN # | Closed | 2024-08-19 | 2024-12-31 | 10.55% | 1866.78 | 0 | 1866.78 | 100% | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHYAS | NGC-240096-2L01565 - GIPP PRISMA Nov-Dec (Expansion) - 006Ka00000NYUhMIAX # | Rejected | 2024-10-24 | 2024-12-31 | 0% | 0 | 181.18 | -181.18 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHYHY | L01565/ NGC-240112-4 / GIPP Pricing Data (Q4 2025 - Negative CN)) /006gR000002I9q5QAC# | Active | 2024-12-01 | 2025-12-31 | 23.23% | 349065.84 | 220734.84 | 128331 | 36.76% | 373508.18 | 264045.39 | 109462.79 | 29.31% | 394340.76 | 308260.98 | 86079.78 | 21.83% | 456589.22 | 267081.97 | 189507.25 | 41.5%
L01565 | UKAHYMU | L01565/NGC-240224/GIPP Technical Roadmap & TT Support/006Ka00000NZ4uSIAT | Active | 2024-12-01 | 2026-02-27 | 9.216% | 0 | 0 | 0 | #DIV/0! | 0 | 42139.1 | -42139.1 | #DIV/0! | 188019.5 | 133735.13 | 54284.37 | 28.87% | 127560.85 | 117170.41 | 10390.44 | 8.145% | MPOC
L01565 | UKAHYMZ | L01565/ NGC-240114-1/GIPP Polaris H2 2025 (Renewal)/006Ka00000NYaG8IAL# | Active | 2024-12-01 | 2025-12-31 | 12.71% | 551021.45 | 396332.97 | 154688.48 | 28.07% | 547294.36 | 365176.08 | 182118.28 | 33.28% | 860467.71 | 694514.89 | 165952.82 | 19.29% | 858832.83 | 679632.2 | 179200.63 | 20.87%
L01565 | UKAHYUA | L01565/NGC-240115-1/- GIPP Value Orchestration H1 25 -Negative CN(Renewal)/006Ka00000NZOBUIA5# | Closed | 2025-01-01 | 2025-06-30 | -5.881% | 35605.09 | 34977.65 | 627.44 | 1.762% | 0 | 2551.04 | -2551.04 | #DIV/0! | 0 | 527.77 | -527.77 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAHYVA | L01565/NGC-240114-1/GIPP Polaris H2 (Renewal)/006Ka00000NYaG8IAL# | Active | 2024-12-01 | 2025-12-31 | 17.39% | 118232.76 | 71618.57 | 46614.19 | 39.43% | 116087.91 | 27126.57 | 88961.34 | 76.63% | 128080.99 | 65309.04 | 62771.95 | 49.01% | 128080.98 | 94143.26 | 33937.72 | 26.5%
L01565 | UKAHYVM | L01565/NGC-240096-7/ GIPP PRISMA (Q4 2025 - Negative CN)/006gR000002GOQEQA4# | Active | 2024-11-13 | 2025-12-31 | 37.81% | 157872.18 | 76922.91 | 80949.27 | 51.28% | 209459.26 | 101493.33 | 107965.93 | 51.55% | 170955.81 | 106376.53 | 64579.28 | 37.78% | 51270.62 | 42491.65 | 8778.97 | 17.12%
L01565 | UKAHYVN | L01565 - NGC-240096-5-GIPP PRISMA H2 2025 (Renewal)-006Ka00000NZm2IIAT# | Active | 2024-11-13 | 2025-12-31 | 9.38% | 70488.15 | 37950.73 | 32537.42 | 46.16% | 74912.77 | 79805.31 | -4892.54 | -6.531% | 83335.75 | 54078.4 | 29257.35 | 35.11% | 70365.9 | 55466.63 | 14899.27 | 21.17%
L01565 | UKAHZFY | L01565 -NGC-240108-1-Bioverse H2 2025 (Renewal)-006Ka00000NYowmIAD# | Active | 2025-01-01 | 2025-12-31 | 17.89% | 45658.77 | 28765.39 | 16893.38 | 37% | 45658.77 | 30218.25 | 15440.52 | 33.82% | 44275.18 | 29400.2 | 14874.98 | 33.6% | 47042.38 | 25979.79 | 21062.59 | 44.77%
L01565 | UKAHZOH | L01565 - NGC-240107-Dataworx Central Team 2025 (Renewal)-0063h00000MkUoYAAV # | Active | 2025-01-01 | 2025-12-31 | 19.22% | 18865.83 | 14807.61 | 4058.22 | 21.51% | 20189.75 | 16340.03 | 3849.72 | 19.07% | 20520.72 | 16022.59 | 4498.13 | 21.92% | 16585.99 | 11592.17 | 4993.82 | 30.11%
L01565 | UKAIBLF | L01565 - GIPP Pricing Data (2H '25 Renewal)# | Rejected | 2025-04-14 | 2025-06-27 | 0% | 0 | 0 | 0 | #DIV/0! | 0 | -254.27 | 254.27 | #DIV/0! | 0 | 225.22 | -225.22 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAIBLG | L01565 - GIPP PRISMA H2 2025 (Renewal)# | Rejected | 2025-04-28 | 2025-06-27 | 0% | 0 | 0 | 0 | #DIV/0! | 0 | -23.15 | 23.15 | #DIV/0! | 0 | 95.1 | -95.1 | #DIV/0! |  |  | 0 | #DIV/0!
L01565 | UKAICTW | L01565_NGC-240112-2_L01565 - GIPP Pricing Data (H2 2025 - CN)_006gR000001JZRKQA4 | Pre-contract no bill | 2025-07-14 | 2025-10-31 | 0% | [8 empty] | 0 | 12523.65 | -12523.65 | #DIV/0! | 0 | 10508.51 | -10508.51 | #DIV/0!
L01565 | UKAICYJ | L01565 - NGC-250053- GIPP TravelCenters of America 2025 /006gR000001ao4CQAQ # | Active | 2025-08-18 | 2025-12-31 | 44.34% | [8 empty] | 0 | 3429.2 | -3429.2 | #DIV/0! | 56433.73 | 20973.04 | 35460.69 | 62.84%
L01565 | UKAICYP | L01565/NGC-240224-2 /006gR0000019h3dQAA/- GIPP Technical Roadmap & TT Support (July '25 CN)# | Active | 2025-07-01 | 2025-12-31 | 39.03% | [8 empty] | 0 | 0 | 0 | #DIV/0! | 70391 | 45817.14 | 24573.86 | 34.91% | MPOC
L01565 | UKAIEEW | L01565-NGC-250054-Colombia Company-006Ka00000QVtCaIAL # | Active | 2025-11-03 | 2026-10-16 | 34.7% | [12 empty] | 0 | 10130.71 | -10130.71 | #DIV/0! | MPOC
Grand Total | [6 empty] | 1296443.53 | 1063167.97 | 233275.56 | 17.99% | 1395299.83 | 1098224.39 | 297075.44 | 21.29% | 1889996.42 | 1574695.83 | 315300.59 | 16.68% | 1883153.5 | 1601376.13 | 281777.37 | 14.96%

## STS -2026
|  |  | STS Total - |  |  |  |  | 13797003.871 | 10728778.3285 | 3068225.5425 | 22.24% | 13797003.871 | 10728778.3285 | 3068225.5425 | 22.24%
[8 empty] | 8901292.82 | 6921792.47 | 1979500.35 | 22.24% | 8901292.82 | 6921792.47 | 1979500.35 | 22.24%
Legal contract number | WBS short ID | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | Plan GP % | 2026-1Q revenue | 2026-1Q cost | 2026-1Q GP | 2026-1Q GP% | 2026-2Qrevenue | 2026-2Qcost | 2026-2QGP | 2026-2QGP%
006GR000002Z0D | 030-PZP | C.26JVZ.001 | ST&S Cross Portfolio 2026 | Active | 2026-01-05 | 2026-12-31 | 7.519% | 43241.37 | 30322.6 | 12918.77 | 29.88% | 43241.37 | 30322.6 | 12918.77 | 29.88%
006GR000002Z0D | 031-9NX | C.26JVZ.003 | ST&S TF&T - WAF Ancillaries Extension | Active | 2026-03-16 | 2026-06-30 | 17.59% | 0 | 10844.68 | -10844.68 | #DIV/0! | 0 | 10844.68 | -10844.68 | #DIV/0!
006GR0000034VRW | 030-G89 | C.26JRZ.001 | Data & Analytics Platform Enablement 202 | Active | 2026-01-01 | 2026-03-31 | 7.829% | 18047.41 | 14164.14 | 3883.27 | 21.52% | 18047.41 | 14164.14 | 3883.27 | 21.52%
006KA00000PFHJ4 | 030-W6P | C.26K1J.001 | ITK Silverstone - Execute 2026-2028 (IND | Active | 2026-01-01 | 2028-12-29 | 16.54% | 1225645 | 896290.12 | 329354.88 | 26.87% | 1225645 | 896290.12 | 329354.88 | 26.87%
006KA00000PFHJ4 | 030-X2T | C.26K1J.002 | AM | Active | 2026-01-01 | 2028-12-29 | 0% | 0 | 17307.28 | -17307.28 | #DIV/0! | 0 | 17307.28 | -17307.28 | #DIV/0!
L01560 | 030-8WX | C.26GBL.039 | L01560 - TF - Risk Dashboard - Ph2 | Pre-contract no bill | 2026-01-02 | 2026-02-27 | 0% | 0 | 19612.94 | -19612.94 | #DIV/0! | 0 | 19612.94 | -19612.94 | #DIV/0!
L01560 | 030-W00 | C.26GBL.041 | TF - Risk Dashboard - Ph3 | Active | 2026-01-01 | 2026-02-06 | 16.2% | 21517.53 | 18266.43 | 3251.1 | 15.11% | 21517.53 | 18266.43 | 3251.1 | 15.11%
L01560 | UKAGUGX | C.26GBL.001 | AM | Active | 2020-06-29 | 2026-12-31 | 0% | 0 | 140625.97 | -140625.97 | #DIV/0! | 0 | 140625.97 | -140625.97 | #DIV/0!
L01560 | UKAHSWZ | C.26GBL.003 | L01560 - NGC-230148-1 - RPT&I Cost Manag | Technically completed | 2023-11-15 | 2025-07-31 | 19.59% | 0 | 100.73 | -100.73 | #DIV/0! | 0 | 100.73 | -100.73 | #DIV/0!
L01560 | UKAHUCV | C.26GBL.004 | ST&S TF - Risk Dashboard - Ph1 | Active | 2023-11-27 | 2026-05-29 | 17.85% | 210751 | 121508.18 | 89242.82 | 42.35% | 210751 | 121508.18 | 89242.82 | 42.35%
L01560 | UKAHUKP | C.26GBL.005 | L01560 - NGC-240030-2-GPT Hyperion - Pow | Active | 2024-03-01 | 2026-12-31 | 25.16% | 207485 | 30168.89 | 177316.11 | 85.46% | 207485 | 30168.89 | 177316.11 | 85.46%
L01560 | UKAHVRH | C.26GBL.006 | L01560 - NGC-240057-4 -ITK Silverstone - | Technically completed | 2024-05-13 | 2025-10-31 | 12.97% | 0 | -485.32 | 485.32 | #DIV/0! | 0 | -485.32 | 485.32 | #DIV/0!
L01560 | UKAHXNG | C.26GBL.007 | L01560/NGC-240102/RPT&I Nigeria /006Ka00 | Technically completed | 2024-10-01 | 2025-12-31 | 11.99% | 0 | 4373.18 | -4373.18 | #DIV/0! | 0 | 4373.18 | -4373.18 | #DIV/0!
L01560 | UKAHYPJ | C.26GBL.010 | L01560 - NGC-240158-1 -- TF&T - Finance | Technically completed | 2024-12-02 | 2025-12-31 | 16.41% | 56121.12 | 629.94 | 55491.18 | 98.88% | 56121.12 | 629.94 | 55491.18 | 98.88%
L01560 | UKAHYXI | C.26GBL.011 | L01560 - NGC-240160-1 -RPT UX Strategy H | Technically completed | 2025-01-13 | 2025-12-31 | 14.44% | 0.01 | 0 | 0.01 | 100% | 0.01 | 0 | 0.01 | 100%
L01560 | UKAHZKP | C.26GBL.012 | L01560 - GPT - Brazil Nfe / 006Ka00000NW | Technically completed | 2025-01-01 | 2025-12-05 | 17.18% | 0 | 28.29 | -28.29 | #DIV/0! | 0 | 28.29 | -28.29 | #DIV/0!
L01560 | UKAHZKR | C.26GBL.013 | L01560 - -NGC-240164-3TF&T - ARC Exten | Technically completed | 2025-01-02 | 2025-12-31 | 18.86% | 47768.85 | 2064.52 | 45704.33 | 95.68% | 47768.85 | 2064.52 | 45704.33 | 95.68%
L01560 | UKAIANF | C.26GBL.016 | L01560/NGC-250012/ ST&S Silverstone - AN | Technically completed | 2025-04-01 | 2025-11-30 | 22.16% | 0 | 27996.96 | -27996.96 | #DIV/0! | 0 | 27996.96 | -27996.96 | #DIV/0!
L01560 | UKAIBWF | C.26GBL.018 | L01560/NGC-250019/ST&S Brazil Marine gas | Active | 2025-06-02 | 2026-07-31 | 31.32% | 107554.26 | 91151.55 | 16402.71 | 15.25% | 107554.26 | 91151.55 | 16402.71 | 15.25%
L01560 | UKAIBWY | C.26GBL.019 | L01560/NGC-250029/ ST&S BR Tax Reforms/0 | Active | 2025-06-16 | 2026-02-27 | 16.84% | 270476.44 | 223554.55 | 46921.89 | 17.35% | 270476.44 | 223554.55 | 46921.89 | 17.35%
L01560 | UKAIBZS | C.26GBL.020 | L01560 - ST&S Trading Finance Derivative | Active | 2025-07-01 | 2026-12-31 | 15.38% | 399788.05 | 313508.21 | 86279.84 | 21.58% | 399788.05 | 313508.21 | 86279.84 | 21.58%
L01560 | UKAICDT | C.26GBL.021 | L01560 -NGC-250020- ST&S Silverstone - E | Active | 2025-06-02 | 2026-07-17 | 15.92% | 517818.62 | 169132.76 | 348685.86 | 67.34% | 517818.62 | 169132.76 | 348685.86 | 67.34%
L01560 | UKAICDX | C.26GBL.022 | L01560 -NGC-250025- ST&S PRI Pre Work/00 | Technically completed | 2025-06-16 | 2025-12-31 | 6.851% | 53646.22 | 2380.34 | 51265.88 | 95.56% | 53646.22 | 2380.34 | 51265.88 | 95.56%
L01560 | UKAICNK | C.26GBL.023 | L01560-NGC-230148-3-RPT&I Cost Managemen | Active | 2025-08-01 | 2026-04-30 | 17.47% | 174314.85 | 98573.41 | 75741.44 | 43.45% | 174314.85 | 98573.41 | 75741.44 | 43.45%
L01560 | UKAICRW | C.26GBL.024 | L01560-NGC-250033 - 2-ST&S Golden Phoeni | Active | 2025-08-18 | 2026-12-18 | -24.59% | 241438.85 | 320190.26 | -78751.41 | -32.62% | 241438.85 | 320190.26 | -78751.41 | -32.62%
L01560 | UKAICTX | C.26GBL.025 | L01560 - NGC-250044-1-Silver Stone - ST& | Active | 2025-08-18 | 2026-06-30 | 17.25% | 219215 | 174624.21 | 44590.79 | 20.34% | 219215 | 174624.21 | 44590.79 | 20.34%
L01560 | UKAIDEU | C.26GBL.026 | L10560 - NGC-250049-ARC Finance Process | Active | 2025-10-01 | 2026-04-30 | 4.567% | 295107.49 | 279996.88 | 15110.61 | 5.12% | 295107.49 | 279996.88 | 15110.61 | 5.12%
L01560 | UKAIDPO | C.26GBL.027 | L01560 - NGC-250055-/ST&S GPTI Endur Set | Technically completed | 2025-10-01 | 2025-12-31 | 18.15% | 19237.59 | 0 | 19237.59 | 100% | 19237.59 | 0 | 19237.59 | 100%
L01560 | UKAIDXY | C.26GBL.029 | L01560/NGC-250070/ST&S Quantum Pre Work | Active | 2025-11-10 | 2026-06-30 | 16.15% | 1059524.39 | 854881.26 | 204643.13 | 19.31% | 1059524.39 | 854881.26 | 204643.13 | 19.31%
L01560 | UKAIEFJ | C.26GBL.030 | System Enhancements | Active | 2025-11-17 | 2026-08-07 | 0% | 0 | 21573.88 | -21573.88 | #DIV/0! | 0 | 21573.88 | -21573.88 | #DIV/0!
L01560 | UKAIEFQ | C.26GBL.031 | L01560 - NGC-250071-SAP Interface Automa | Active | 2025-11-17 | 2026-12-28 | 16.66% | 119362 | 71293.28 | 48068.72 | 40.27% | 119362 | 71293.28 | 48068.72 | 40.27%
L01560 | UKAIEIJ | C.26GBL.032 | L01560 -NGC-250072- ITK Silverstone - Eu | Active | 2025-11-17 | 2026-02-27 | 18.67% | 1912604.47 | 1659102.72 | 253501.75 | 13.25% | 1912604.47 | 1659102.72 | 253501.75 | 13.25%
L01560 | UKAIELQ | C.26GBL.033 | L01560 -NGC-250088- ST&S - Low Carbon Mi | Active | 2025-11-20 | 2026-10-30 | 16.64% | 131428 | 93977.32 | 37450.68 | 28.5% | 131428 | 93977.32 | 37450.68 | 28.5%
L01560 | UKAIEWP | C.26GBL.034 | L01560 - GPTI Endur Settlements# | Active | 2026-01-02 | 2026-12-31 | -20.62% | 107628 | 46967.41 | 60660.59 | 56.36% | 107628 | 46967.41 | 60660.59 | 56.36%
L01560 | UKAIEWS | C.26GBL.035 | L01560 - ST&S Golden Phoenix - Core Team | Pre-contract no bill | 2026-01-01 | 2026-02-27 | 0% | 0 | 558.99 | -558.99 | #DIV/0! | 0 | 558.99 | -558.99 | #DIV/0!
L01560 | UKAIEXM | C.26GBL.038 | TF - Risk Dashboard - Ph3 | Pre-contract no bill | 2026-01-01 | 2026-03-31 | 0% | 0 | 529.39 | -529.39 | #DIV/0! | 0 | 529.39 | -529.39 | #DIV/0!
L01565 | UKAHHSG | C.26HWM.001 | PMO | Active | 2022-01-01 | 2026-12-31 | 0% | 0 | 62186.51 | -62186.51 | #DIV/0! | 0 | 62186.51 | -62186.51 | #DIV/0!
L01565 | UKAHHSH | C.26HWM.002 | AM | Active | 2022-01-01 | 2026-12-31 | 0% | 0 | -18393.88 | 18393.88 | #DIV/0! | 0 | -18393.88 | 18393.88 | #DIV/0!
L01565 | UKAHYHY | C.26HWM.003 | L01565/ NGC-240112-4 / GIPP Pricing Data | Technically completed | 2024-12-01 | 2025-12-31 | 23.23% | 17949.71 | 850.01 | 17099.7 | 95.26% | 17949.71 | 850.01 | 17099.7 | 95.26%
L01565 | UKAHYMU | C.26HWM.004 | L01565/NGC-240224/GIPP Technical Roadmap | Active | 2024-12-01 | 2026-02-27 | 9.216% | 278075.61 | 78473.64 | 199601.97 | 71.78% | 278075.61 | 78473.64 | 199601.97 | 71.78%
L01565 | UKAHYMZ | C.26HWM.005 | L01565 - NGC-240114-2-GIPP Polaris 2026 | Active | 2024-12-01 | 2026-06-30 | 13.95% | 313223.28 | 539888.65 | -226665.37 | -72.37% | 313223.28 | 539888.65 | -226665.37 | -72.37%
L01565 | UKAHYVA | C.26HWM.007 | L01565 - NGC-240114-2-GIPP Polaris 2026 | Active | 2024-12-01 | 2026-06-30 | 19.08% | 139406.89 | 157541.98 | -18135.09 | -13.01% | 139406.89 | 157541.98 | -18135.09 | -13.01%
L01565 | UKAHYVM | C.26HWM.008 | L01565/NGC-240096-7/ GIPP PRISMA (Q4 20 | Technically completed | 2024-11-13 | 2025-12-31 | 37.81% | 0.06 | 2329.72 | -2329.66 | -3882767% | 0.06 | 2329.72 | -2329.66 | -3882767%
L01565 | UKAHYVN | C.26HWM.009 | L01565 - NGC-240096-5-GIPP PRISMA H2 202 | Technically completed | 2024-11-13 | 2025-12-31 | 9.38% | 0.01 | 5980.53 | -5980.52 | -59805200% | 0.01 | 5980.53 | -5980.52 | -59805200%
L01565 | UKAHZFY | C.26HWM.010 | L01565 -NGC-240108-1-Bioverse H2 2025 (R | Technically completed | 2025-01-01 | 2025-12-31 | 17.89% | 0 | 1788.54 | -1788.54 | #DIV/0! | 0 | 1788.54 | -1788.54 | #DIV/0!
L01565 | UKAICYP | C.26HWM.013 | L01565/NGC-240224-2 /006gR0000019h3dQAA/ | Technically completed | 2025-07-01 | 2025-12-31 | 39.03% | 37124.99 | -801.12 | 37926.11 | 102.2% | 37124.99 | -801.12 | 37926.11 | 102.2%
L01565 | UKAIEEW | C.26HWM.014 | L01565-NGC-250054-Colombia Company-006Ka | Active | 2025-11-03 | 2026-10-16 | 34.7% | 346971.95 | 143096.32 | 203875.63 | 58.76% | 346971.95 | 143096.32 | 203875.63 | 58.76%
L01565 | UKAIEMZ | C.26HWM.015 | L01565 - NGC-250076 Bioverse Q1 2026 /06 | Active | 2026-01-01 | 2026-12-31 | 18.18% | 47586.83 | 33277.38 | 14309.45 | 30.07% | 47586.83 | 33277.38 | 14309.45 | 30.07%
L01565 | UKAIEQC | C.26HWM.016 | L01565 /NGC-250078/GIPP Pricing Data & A | Active | 2026-01-26 | 2026-06-30 | 12.31% | 261231.97 | 159851.23 | 101380.74 | 38.81% | 261231.97 | 159851.23 | 101380.74 | 38.81%
L01565 | UKAIEWR | C.26HWM.017 | Data & Analytics Platform Enablement 202 | Pre-contract no bill | 2026-01-01 | 2026-01-30 | 0% | 0 | -92.99 | 92.99 | #DIV/0! | 0 | -92.99 | 92.99 | #DIV/0!
Grand Total | [7 empty] | 8901292.82 | 6921792.47 | 1979500.35 | 22.24% | 8901292.82 | 6921792.47 | 1979500.35 | 22.24%

## Q1 2026 (hidden)
|  | L01560 + L01565 Total - |  |  |  |  | 6131612.0935 | 5382829.243 | 748782.8505 | 12.21%
[7 empty] | 5551700.503 | 4930566.6315 | 621133.8715 | 11.19%
[7 empty] | 3581742.26 | 3181010.73 | 400731.53 | 11.19%
Legal contract number | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | Sum of Plan GP% | 2026-1Q revenue | 2026-1Q cost | 2026-1Q GP | 2026-1Q GP% | Type | Remarks
L01560 | UKAGUGX | AM | Active | 2020-06-29 | 2026-12-31 | 0% | 0 | 0 | 0 | #DIV/0!
L01560 | UKAHUCV | L01563 -NGC-230403-2- TF&T - HARP 2025 - 0063h00000MCEawAAH # | Active | 2023-11-27 | 2025-12-31 | 18.93% | 18427 | 15304.72 | 3122.28 | 16.94%
L01560 | UKAHXNG | L01560/NGC-240102/RPT&I Nigeria /006Ka00000NUql7IAD# | Active | 2024-10-01 | 2025-12-31 | 11.99% | 0 | 17637.26 | -17637.26 | #DIV/0!
L01560 | UKAHYPJ | L01560 - NGC-240158-1 -- TF&T - Finance Process Automation - CR 1 / 006gR0000009fyPQAQ # | Active | 2024-12-02 | 2025-12-31 | 16.41% | 3267 | 2785.2 | 481.8 | 14.75%
L01560 | UKAIBWF | L01560/NGC-250019/ST&S Brazil Marine gasoi/006Ka00000QVtCzIAL# | Active | 2025-06-02 | 2026-03-27 | 31.32% | 27056.26 | 130584.25 | -103527.99 | -382.6%
L01560 | UKAIBWY | L01560/NGC-250029/ ST&S BR Tax Reforms/006Ka00000QVtCuIAL# | Active | 2025-06-16 | 2026-02-27 | 16.84% | 141216 | 120741.4 | 20474.6 | 14.5%
L01560 | UKAIBZS | L01560 - ST&S Trading Finance Derivatives Activity/006Ka00000QVkVhIAL# | Active | 2025-07-01 | 2026-12-31 | 15.38% | 373204 | 325399.42 | 47804.58 | 12.81%
L01560 | UKAICDT | L01560 -NGC-250020- ST&S Silverstone - Europe and IDM /006gR000000JYagQAG # | Active | 2025-06-02 | 2026-07-17 | 15.92% | 211873 | 185544.38 | 26328.62 | 12.43%
L01560 | UKAICDX | L01560 -NGC-250025- ST&S PRI Pre Work/006Ka00000NW82rIAD# | Active | 2025-06-16 | 2025-12-31 | 6.851% | 61027 | 56710.86 | 4316.14 | 7.073%
L01560 | UKAICNK | L01560/NGC-230148-2/ RPT Cost Management Marine CR/006Ka00000QWBagIAH# | Active | 2025-08-01 | 2026-01-31 | 17.43% | 32379 | 27380.52 | 4998.48 | 15.44%
L01560 | UKAICRW | L01560-NGC-250033 - 1-ST&S Golden Phoenix (CN1 - Data Scientists)-006gR000001VfUZQA0 # | Active | 2025-08-18 | 2025-12-19 | 3.935% | 20894 | 20176 | 718 | 3.436%
L01560 | UKAICTX | L01560 - NGC-250044-1-Silver Stone - ST&S Risk Insights /006gR000001odtfQAA # | Active | 2025-08-18 | 2026-06-30 | 17.25% | 116768 | 100410.02 | 16357.98 | 14.01%
L01560 | UKAIDEU | L10560 - NGC-250049-ARC Finance Process Automation-006gR000001Yus2QAC # | Active | 2025-10-01 | 2026-04-30 | 4.567% | 269049 | 260426.8 | 8622.2 | 3.205%
L01560 | UKAIDPO | L01560 - NGC-250055-/ST&S GPTI Endur Settlements/006gR0000028XyYQAU# | Active | 2025-10-01 | 2025-12-31 | 18.15% | 2078 | 1754.08 | 323.92 | 15.59%
L01560 | UKAIDXY | L01560/NGC-250070/ST&S Quantum Pre Work CR1/006gR000002IK0jQAG# | Active | 2025-11-10 | 2026-06-30 | 24.08% | 668002 | 527366.74 | 140635.26 | 21.05%
L01560 | UKAIEIJ | L01560 -NGC-250072- ITK Silverstone - Europe and IDM - CR2 / 006gR000001r5nOQAQ | Active | 2025-11-17 | 2026-02-27 | 18.67% | 1636502 | 1388789.08 | 247712.92 | 15.14%
Grand Total | [6 empty] | 3581742.26 | 3181010.73 | 400731.53 | 11.19%
[7 empty] | 579911.5905 | 452262.6115 | 127648.979 | 22.01%
[7 empty] | 374136.51 | 291782.33 | 82354.18 | 22.01%
Legal contract number | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | Plan GP % | 2026-1Q revenue | 2026-1Q cost | 2026-1Q GP | 2026-1Q GP% | Type | Remarks
L01565 | UKAHHSG | PMO | Active | 2022-01-01 | 2025-12-31 |  | 0 | 0 | 0 | #DIV/0!
L01565 | UKAHHSH | AM | Active | 2022-01-01 | 2025-12-31 |  | 0 | 0 | 0 | #DIV/0!
L01565 | UKAHYHY | L01565/ NGC-240112-4 / GIPP Pricing Data (Q4 2025 - Negative CN)) /006gR000002I9q5QAC# | Active | 2024-12-01 | 2025-12-31 | 23.23% | 17949.7 | 0 | 17949.7 | 100%
L01565 | UKAHYMU | L01565/NGC-240224/GIPP Technical Roadmap & TT Support/006Ka00000NZ4uSIAT | Active | 2024-12-01 | 2026-02-27 | 9.216% | 80172 | 74447.22 | 5724.78 | 7.141%
L01565 | UKAHYMZ | L01565/ NGC-240114-1/GIPP Polaris H2 2025 (Renewal)/006Ka00000NYaG8IAL# | Active | 2024-12-01 | 2025-12-31 | 12.71% | 0 | 34639.97 | -34639.97 | #DIV/0!
L01565 | UKAHZFY | L01565 -NGC-240108-1-Bioverse H2 2025 (Renewal)-006Ka00000NYowmIAD# | Active | 2025-01-01 | 2025-12-31 | 17.89% | 0 | 1544.4 | -1544.4 | #DIV/0!
L01565 | UKAICYJ | L01565 - NGC-250053- GIPP TravelCenters of America 2025 /006gR000001ao4CQAQ # | Active | 2025-08-18 | 2025-12-31 | 44.34% | 0 | 341.46 | -341.46 | #DIV/0!
L01565 | UKAICYP | L01565/NGC-240224-2 /006gR0000019h3dQAA/- GIPP Technical Roadmap & TT Support (July '25 CN)# | Active | 2025-07-01 | 2025-12-31 | 39.03% | 2177 | -1156 | 3333 | 153.1%
L01565 | UKAIEEW | L01565-NGC-250054-Colombia Company-006Ka00000QVtCaIAL # | Active | 2025-11-03 | 2026-10-16 | 34.7% | 226251 | 150562.48 | 75688.52 | 33.45%
L01565 | UKAIEMZ | L01565 - NGC-250076 Bioverse Q1 2026 /06Ka00000NZWv8IAH # | Active | 2026-01-01 | 2026-12-31 | 18.18% | 47586.81 | 31402.8 | 16184.01 | 34.01%
Grand Total | [6 empty] | 374136.51 | 291782.33 | 82354.18 | 22.01%

## Qtr Rev Variance (hidden)
May'25 FC Cycle | [6 empty] | May Submission |  |  |  | Apr Submission
[7 empty] | 2263343.6505 | 2907847.6625 | 3391863.14 | 8563054.453 | 2347436.6252 | 2712212.2902 | 3296603.7937 | 8356252.709 | 206801.744
Legal contract number | WBS ID | WBS short description | WBS IPPF status | WBS start date | WBS end date | IPPF T&M indicator | 2025-Apr Rev | 2025-May Rev | 2025-Jun Rev | 2025-Q2 Rev | 2025-Apr Rev | 2025-May Rev | 2025-Jun Rev | 2025-Q2 Rev | Q2 Delta | Remarks | Remarks (Saurav)
L01560 | UKAHRHQ | L01560 - NGC-230336-3 - TF&T Supply Chain Finance CR2 / 006Ka00000NTjEhIAL # | Active | 2023-08-13 | 2025-06-27 | MPOC | 69601.86 | 93968 | 123683 | 287252.86 | 69429 | 96773 | 120966 | 287168 | 84.86
L01560 | UKAHSWZ | L01560 - NGC-230148-1 - RPT&I Cost Management Marine CR / 0063h00000MCY3rAAH # | Active | 2023-11-15 | 2025-07-31 | MPOC | 29581.63 | 56868 | 48853 | 135302.63 | 26089.63 | 34214.35 | 41226.37 | 101530.35 | 33772.28 | Apr was more cost, impacted more Rev in Q2
L01560 | UKAHUCV | L01563 -NGC-230403-2- TF&T - HARP 2025 - 0063h00000MCEawAAH # | Active | 2023-11-27 | 2025-12-31 | MPOC | 56873.56 | 77730 | 103170.5 | 237774.06 | 61001.7 | 75400.6 | 94251.2 | 230653.5 | 7120.56
L01560 | UKAHUKP | L01560 - NGC-240030-1-GPT Hyperion - Power and Brazil Wholesalel / 0063h00000MClvMAAT # | Active | 2024-03-01 | 2026-06-30 | MPOC | 34290.03 | 140136 | 193343 | 367769.03 | 19867 | 24180.6 | 62296.4 | 106344 | 261425.03 | More cost forecasted, impacted more Rev in Q2 | May, Jun & Jul Milestone cancelled and next revised milestone is 05th Sep
L01560 | UKAHVRH | L01560 - NGC-240057-4 -ITK Silverstone - Define 2 / 006Ka00000NWCzsIAH # | Active | 2024-05-13 | 2025-10-31 | MPOC | 480352.8 | 443407 | 575856 | 1499615.8 | 397423.03 | 422182.94 | 521565.18 | 1341171.15 | 158444.65 | Release some cost buffer, increased Q2 Rev
L01560 | UKAHXNG | L01560/NGC-240102/RPT&I Nigeria /006Ka00000NUql7IAD# | Active | 2024-10-01 | 2025-07-11 | Milestone | 58832.13 | 0 | 0 | 58832.13 | 58832 | 58832 | 58832 | 176496 | -117663.87 | Currently the project is onhold and IBM working on zero value extension till Nov 25, hence there is no hours added for forecast. Added 62.5/month cost in Jul to Oct
L01560 | UKAHYAH | L01560 NGC-240128/ GPT LNG Transformation/006Ka00000NW6qLIAT# | Active | 2024-11-01 | 2025-07-31 | MPOC | 11572.85 | 22723 | 26669 | 60964.85 | 12837.28 | 17238.18 | 22191.35 | 52266.81 | 8698.04 | IBM working on zero value extension till Nov 25 and we have more contigency buffer 288K
L01560 | UKAHYHH | L01560/ NGC-240127/RPT - Brazil Crude/006Ka00000NW6quIAD# | Active | 2024-11-25 | 2025-06-30 | MPOC | 85999.25 | 113017 | 45348 | 244364.25 | 98222 | 103252 | 42208 | 243682 | 682.25
L01560 | UKAHYPJ | L01560 - NGC-240158 - TF&T - Oman NAI and Finance Process Automation / 006Ka00000NW82mIAD # | Active | 2024-12-02 | 2025-12-31 | MPOC | 57363.63 | 93787 | 71577 | 222727.63 | 69335.6 | 70347.74 | 87934.68 | 227618.02 | -4890.39 | Not accrued due to clip level, hence forecasted more rev in May and Jun cost forecast decreased.
L01560 | UKAHYXI | L01560 - NGC-240160 - RPT&I RPT UX Strategy / 006Ka00000NVuzuIAD # | Active | 2025-01-13 | 2025-06-30 | MPOC | -13631.56 | 109267 | 81821 | 177456.44 | 45998.48 | 70050.72 | 87097.71 | 203146.91 | -25690.47 | Not accrued due to clip level, hence forecasted more rev in May
L01560 | UKAHZKP | L01560 - GPT - Brazil Nfe / 006Ka00000NWK22IAH | Active | 2025-01-01 | 2025-12-05 | MPOC | 27516.52 | 30698 | 94470 | 152684.52 | 25517.01 | 26409.53 | 88996.47 | 140923.01 | 11761.51
L01560 | UKAHZKR | L01560/NGC-240164-1/TF ARC Transformation - CR/006Ka00000QWOU9IAP# | Active | 2025-01-02 | 2025-06-30 | MPOC | 3490 | 0 | 990 | 4480 | 3490 | 0 | 990 | 4480 | 0
L01560 | UKAHZKR | L01560/NGC-240164-1/TF ARC Transformation - CR/006Ka00000QWOU9IAP# | ISC | 2025-01-02 | 2025-06-30 | MPOC | 989.93 | 47098 | 85040 | 133127.93 | 0 | 95750.4323 | 100000.0387 | 195750.471 | -62622.541 | ISC new entry for May submission, Rev calculated based on MPOC
L01560 | UKAHZQI | L01560/NGC-240161/TF&T - E2E Process Management/006Ka00000NW89YIAT# | Active | 2025-01-20 | 2025-07-18 | MPOC | 50173.63 | 50643 | 65416 | 166232.63 | 48029.97 | 49396.77 | 61745.97 | 159172.71 | 7059.92
L01560 | UKAHZRH | L01560/NGC-240226/L01560 - GPT SRA SAP Canada/006Ka00000NWiKcIAL# | Active | 2025-01-01 | 2025-07-31 | MPOC | 41039.87 | 76206 | 96867 | 214112.87 | 29793.51 | 77264.4 | 96580.51 | 203638.42 | 10474.45
L01560 | UKAIANF | L01560/NGC-250012/ ST&S Silverstone - ANZ/006Ka00000QVniqIAD# | ISC | 2025-04-01 | 2025-11-30 | MPOC | 0 | 111471 | 76621 | 188092 | 90000.0387 | 90000.0387 | 90000.0387 | 270000.1161 | -81908.1161 | ISC new entry for May submission, Rev calculated based on MPOC
L01560 | UKAIBDZ | L01560-NGC-250014-GPTI Euro Cons Unit Migration /006Ka00000QWgUuIAL # | ISC | 2025-05-01 | 2025-08-15 | Milestone | 0 | 0 | 39153.47 | 39153.47 | 0 | 20000.0065 | 25000.0065 | 45000.0129 | -5846.5429 | ISC new entry for May submission, Rev calculated based on MPOC
L01565 | UKAHTTS | L01565 - NGC-230041-3 - L01565 - GIPP Polaris 2024 H2 (Renewal)/ 0063h00000LW7TmAAL # | Closed | 2024-01-01 | 2024-12-31 | No | 8188.83 | 0 | 0 | 8188.83 | 0 | 0 | 0 | 0 | 8188.83
L01565 | UKAHYHY | L01565/NGC-240114 / GIPP Pricing Analytics & AI 1H '25 (Renewal)/0063h00000Lp7XyAAJ# | Active | 2024-12-01 | 2025-06-27 | Milestone | 109323.15 | 87459 | 131187 | 327969.15 | 109323 | 87459 | 131187 | 327969 | 0.15
L01565 | UKAHYMU | L01565/NGC-240224/GIPP Technical Roadmap & TT Support/006Ka00000NZ4uSIAT | Active | 2024-12-01 | 2025-10-31 | MPOC | 0 | 0 | 0 | 0 | 0 | 0 | 55734 | 55734 | -55734 | Q2 Rev pushed to Q3 due to not sufficient cost
L01565 | UKAHYMZ | L01565/240114/ GIPP Polaris H1 2025 (Renewal)/0063h00000Lp7XzAAJ# | Active | 2024-12-01 | 2025-06-30 | No | 186876.85 | 180847.62 | 179570.51 | 547294.98 | 180604.22 | 183345.18 | 183345.18 | 547294.58 | 0.4
L01565 | UKAHYVA | L01565/NGC-240114/GIPP Polaris H1 2025 (Renewal)/0063h00000Lp7XzAAJ# | Active | 2024-12-01 | 2025-06-30 | No | 49436.21 | 36015.04 | 30637 | 116088.25 | 49436 | 36015.04 | 30637 | 116088.04 | 0.21
L01565 | UKAHYVM | L01565/NGC-240096-4/GIPP PRISMA H1 - Mexico CN/006Ka00000NYUhgIAHL# | Active | 2024-11-13 | 2025-06-30 | No | 53189.7 | 53189.7 | 53189.7 | 159569.1 | 53189.7 | 53189.7 | 53189.7 | 159569.1 | 0
L01565 | UKAHYVM | L01565/NGC-240096-4/GIPP PRISMA H1 - Mexico CN/006Ka00000NYUhgIAHL# | ISC | 2024-11-13 | 2025-06-30 | No | 7001.88 | 13818.1 | 13818.1 | 34638.08 | 18333.3333 | 18333.3333 | 18333.3333 | 55000 | -20361.92 | ISC new entry for May submission, Rev calculated based on MPOC
L01565 | UKAHYVN | L01565 - GIPP PRISMA H1 2025 (Renewal)-006Ka00000NYnA3IAL# | Active | 2024-11-13 | 2025-06-30 | No | 30981.74 | 19174.49 | 24756.54 | 74912.77 | 26171.02 | 21671.02 | 26271.04 | 74113.08 | 799.69
L01565 | UKAHZFY | L01565 -NGC-240108- Bioverse H1 2025 (Renewal)-0063h00000Lp7bnAAB# | Active | 2025-01-01 | 2025-06-30 | Milestone | 15219.59 | 12175.67 | 18263.5 | 45658.76 | 15219.59 | 12175.67 | 18263.5 | 45658.76 | 0
L01565 | UKAHZOH | L01565 - NGC-240107-Dataworx Central Team 2025 (Renewal)-0063h00000MkUoYAAV # | Active | 2025-01-01 | 2025-12-31 | Yes | 5957.63 | 6332.13 | 7998.48 | 20288.24 | 6332.13 | 6332.13 | 7998.48 | 20662.74 | -374.5
Grand Total | [6 empty] | 1460221.71 | 1876030.75 | 2188298.8 | 5524551.26 | 1514475.242 | 1749814.3808 | 2126841.1572 | 5391130.78 | 133420.48

## TCV Vs EAC+Netting (hidden)
Legal contract number | WBS ID | WBS short description | WBS IPPF status | IPPF T&M indicator | WBS start date | WBS end date | Sum of Plan revenue | Sum of TCV Amount (billing currency) | Sum of ITD revenue | Sum of EtC revenue | Sum of EaC revenue | Sum of Plan-EaC | Sum of Tcv-EaC | Remarks
L01560 | UKAHRHQ | L01560 - NGC-230336-3 - TF&T Supply Chain Finance CR2 / 006Ka00000NTjEhIAL # | Active | No | 2023-08-13 | 2025-06-27 | 1367971.14 | 1375087.3 | 1136282.28 | 231689 | 1367971.28 | -0.14 | 7116.02 | Variance due to MSP Fee
L01560 | UKAHSWZ | L01560 - NGC-230148-1 - RPT&I Cost Management Marine CR / 0063h00000MCY3rAAH # | Active | No | 2023-11-15 | 2025-07-31 | 1005924.62 | 1011194.65 | 634894.67 | 371030 | 1005924.67 | -0.05 | 5269.98 | Variance due to MSP Fee
L01560 | UKAHUCV | L01563 -NGC-230403-2- TF&T - HARP 2025 - 0063h00000MCEawAAH # | Active | No | 2023-11-27 | 2025-12-31 | 2090331.62 | 2101167.83 | 1074015.97 | 1016315.43 | 2090331.4 | 0.22 | 10836.43 | Variance due to MSP Fee
L01560 | UKAHUKP | L01560 - NGC-240030-1-GPT Hyperion - Power and Brazil Wholesalel / 0063h00000MClvMAAT # | Active | No | 2024-03-01 | 2026-06-30 | 2765494.7 | 2779722.52 | 373190.28 | 2392304 | 2765494.28 | 0.42 | 14228.24 | Variance due to MSP Fee | Neg CN
L01560 | UKAHVRH | L01560 - NGC-240057-4 -ITK Silverstone - Define 2 / 006Ka00000NWCzsIAH # | Active | No | 2024-05-13 | 2025-10-31 | 6587607.01 | 6623714.73 | 2958932.95 | 3628674 | 6587606.95 | 0.06 | 36107.78 | Variance due to MSP Fee
L01560 | UKAHXNG | L01560/NGC-240102/RPT&I Nigeria /006Ka00000NUql7IAD# | Active | No | 2024-10-01 | 2025-07-11 | 490267.78 | 492979.2 | 343187.45 | 147080 | 490267.45 | 0.33 | 2711.75 | Variance due to MSP Fee
L01560 | UKAHYAH | L01560 NGC-240128/ GPT LNG Transformation/006Ka00000NW6qLIAT# | Active | No | 2024-11-01 | 2025-07-31 | 500761.14 | 503530.55 | 136030.58 | 364730 | 500760.58 | 0.56 | 2769.97 | Variance due to MSP Fee
L01560 | UKAHYHH | L01560/ NGC-240127/RPT - Brazil Crude/006Ka00000NW6quIAD# | Active | No | 2024-11-25 | 2025-06-30 | 650224.02 | 650412.68 | 453300.05 | 196924 | 650224.05 | -0.03 | 188.63
L01560 | UKAHYPJ | L01560 - NGC-240158 - TF&T - Oman NAI and Finance Process Automation / 006Ka00000NW82mIAD # | Active | No | 2024-12-02 | 2025-12-31 | 752248.34 | 756408.62 | 391169.13 | 361079 | 752248.13 | 0.21 | 4160.49 | Variance due to MSP Fee
L01560 | UKAHYXI | L01560 - NGC-240160 - RPT&I RPT UX Strategy / 006Ka00000NVuzuIAD # | Active | No | 2025-01-13 | 2025-06-30 | 372723.15 | 374784.47 | 169251.05 | 203472 | 372723.05 | 0.1 | 2061.42 | Variance due to MSP Fee
L01560 | UKAHZKP | L01560 - GPT - Brazil Nfe / 006Ka00000NWK22IAH | Active | No | 2025-01-01 | 2025-12-05 | 1205711.8 | 1212379.89 | 94404.02 | 1111308 | 1205712.02 | -0.22 | 6667.87 | Variance due to MSP Fee
L01560 | UKAHZKR | L01560/NGC-240164-1/TF ARC Transformation - CR/006Ka00000QWOU9IAP# | Active | No | 2025-01-02 | 2025-06-30 | 385962.34 | 388096.91 | 190212 | 195750 | 385962 | 0.34 | 2134.91 | Variance due to MSP Fee
L01560 | UKAHZQI | L01560/NGC-240161/TF&T - E2E Process Management/006Ka00000NW89YIAT# | Active | No | 2025-01-20 | 2025-07-18 | 379834.75 | 381935.43 | 174286.36 | 205549 | 379835.36 | -0.61 | 2100.07 | Variance due to MSP Fee
L01560 | UKAHZRH | L01560/NGC-240226/L01560 - GPT SRA SAP Canada/006Ka00000NWiKcIAL# | Active | No | 2025-01-01 | 2025-07-31 | 250407.22 | 251792.12 | 57589.67 | 192818 | 250407.67 | -0.45 | 1384.45 | Variance due to MSP Fee
L01560 | UKAIANF | L01560/NGC-250012/ ST&S Silverstone - ANZ/006Ka00000QVniqIAD# | Active | No | 2025-04-01 | 2025-11-30 | 1341373.28 | 1348791.69 | 0 | 1341373 | 1341373 | 0.28 | 7418.69 | Variance due to MSP Fee
L01560 | UKAIBDZ | L01560-NGC-250014-GPTI Euro Cons Unit Migration /006Ka00000QWgUuIAL # | Active | No | 2025-05-01 | 2025-08-15 | 85902.47 | 86377.57 | 0 | 85902.5 | 85902.5 | -0.03 | 475.07 | Variance due to MSP Fee
L01565 | UKAHYHY | L01565/NGC-240114 / GIPP Pricing Analytics & AI 1H '25 (Renewal)/0063h00000Lp7XyAAJ# | Active | No | 2024-12-01 | 2025-06-27 | 677035.24 | 680779.56 | 458388.99 | 218646 | 677034.99 | 0.25 | 3744.57 | Variance due to MSP Fee
L01565 | UKAHYMU | L01565/NGC-240224/GIPP Technical Roadmap & TT Support/006Ka00000NZ4uSIAT | Active | No | 2024-12-01 | 2025-10-31 | 620443.96 | 623875.27 | 0 | 620444 | 620444 | -0.04 | 3431.27 | Variance due to MSP Fee
L01565 | UKAHYMZ | L01565/240114/ GIPP Polaris H1 2025 (Renewal)/0063h00000Lp7XzAAJ# | Active | No | 2024-12-01 | 2025-06-30 | 1131025.26 | 1103400.57 | 770607.27 | 360418.13 | 1131025.4 | -0.14 | -27624.83 | Variance due to MSP Fee+Expense forecasted
L01565 | UKAHYUA | L01565/NGC-240115-1/- GIPP Value Orchestration H1 25 -Negative CN(Renewal)/006Ka00000NZOBUIA5# | Active | No | 2025-01-01 | 2025-06-30 | 35605.1 | 35802 | 35605.09 | 0 | 35605.09 | 0.01 | 196.91 | Variance due to MSP Fee
L01565 | UKAHYVA | L01565/NGC-240114/GIPP Polaris H1 2025 (Renewal)/0063h00000Lp7XzAAJ# | Active | No | 2024-12-01 | 2025-06-30 | 237555.67 | 237555.67 | 170903.92 | 66652.04 | 237555.96 | -0.29 | -0.29
L01565 | UKAHYVM | L01565/NGC-240096-4/GIPP PRISMA H1 - Mexico CN/006Ka00000NYUhgIAHL# | Active | No | 2024-11-13 | 2025-06-30 | 363144.3 | 365956.83 | 229128.76 | 134015.6 | 363144.36 | -0.06 | 2812.47 | Variance due to MSP Fee+799 Less loaded
L01565 | UKAHYVN | L01565 - GIPP PRISMA H1 2025 (Renewal)-006Ka00000NYnA3IAL# | Active | No | 2024-11-13 | 2025-06-30 | 145400.89 | 145400.93 | 101469.89 | 43931.03 | 145400.92 | -0.03 | 0.01
L01565 | UKAHZFY | L01565 -NGC-240108- Bioverse H1 2025 (Renewal)-0063h00000Lp7bnAAB# | Active | No | 2025-01-01 | 2025-06-30 | 91317.53 | 91822.57 | 60878.36 | 30439.17 | 91317.53 | 0 | 505.04 | Variance due to MSP Fee
L01565 | UKAHZOH | L01565 - NGC-240107-Dataworx Central Team 2025 (Renewal)-0063h00000MkUoYAAV # | Active | Yes | 2025-01-01 | 2025-12-31 | 76125.04 | 76546.13 | 24823.46 | 51212.49 | 76035.95 | 89.09 | 510.18 | Variance due to MSP Fee
| Qn | 1. Is there any Negative CN or netting due to project termination..?

## ISC (hidden)
Type | S-Stage | Account ID | Name | Contract # | ISC Id | M1 | M2 | M3 | QTR Revenue | Close Date | PCW Account ID | Status | FG Status | PCW Cost | Findings /Issue | Action reqd(Shankar) | Rev Logic
ISC-Call | Closing |  | L01560 - ST&S Brazil Marine gasoil | L01560 | 006Ka00000QVtCzIAL | 0 | 0 | 116250.05 | 116250.05 | 2025-06-12 |  | In Progress | SOW Created | No cost | Project starts from 2nd June , Milestone date is 18th June | MPOC logic will be considered, it doesn’t look like we can procure the milestone value as initially expected, since the initial cost will appears to be quite low. Given this, we can proceed with moving it to M1 Q3. | Non POC
ISC-Call | Design |  | L01560 - TF&T - Finance Process Automation - CR 1 | L01560 | 006gR0000009fyPQAQ | 0 | 0 | 100750.04 | 100750.04 | 2025-06-26 |  | In Progress | Not created | No cost | Project starts from 1st June , Milestone date is 18th July | Please move the Milestone Revenue to M1 Q3 | MPOC
ISC-Upside | Propose |  | L01565 - B2B Pricing Product Manager | L01565 | 006gR000000KBKHQA4 | 1.55 | 1.55 | 41850.01 | 41853.11 | 2025-06-27 |  | In Progress | Not created | No cost | No Manthan entry as of now | B2B Pricing - Lost the oppt | Lost

## MPOC Model (hidden)
[7 empty] | Forecast |  |  |  | Actual |  |  |  | Diff Rev
[7 empty] | 3062860.016 | 2230248.004 | 832612.012 |  | 3299909.4106 | 2270415.4527 | 1029493.958 |  | 237049.3946
[7 empty] | 1976038.72 | 1438869.68 | 537169.04 | 27.18% | 2128973.8133 | 1464784.163 | 664189.6503 | 31.2%
Con ID | Acc ID | Description | Status | StartDate | EndDate | T&M Flg | Rev_Aug | Cst_Aug | GP | GP% | Rev_Aug | Cst_Aug | GP | GP% | Diff Rev
L01560 | UKAHRHQ | L01560 - NGC-230336-3 - TF&T Supply Chain Finance CR2 / 006Ka00000NTjEhIAL # | Active | 2023-08-13 | 2025-06-27 | POC | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0
L01560 | UKAHSWZ | L01560 - NGC-230148-1 - RPT&I Cost Management Marine CR / 0063h00000MCY3rAAH # | Active | 2023-11-15 | 2025-07-31 | POC | 224520 | 6757.2 | 217762.8 | 96.99% | 224519.7722 | 6757.2 | 217762.5722 | 96.99% | -0.22785
L01560 | UKAHUCV | L01563 -NGC-230403-2- TF&T - HARP 2025 - 0063h00000MCEawAAH # | Active | 2023-11-27 | 2025-12-31 | POC | 74132 | 61562.07 | 12569.93 | 16.96% | 72077.0785 | 60622.325 | 11454.7535 | 15.89% | -2054.9215
L01560 | UKAHUKP | L01560 - NGC-240030-2-GPT Hyperion - Power and Brazil Wholesale CR- 006gR000000LljtQAC # | Active | 2024-03-01 | 2026-12-31 | POC | 118270 | 24417.68 | 93852.32 | 79.35% | 179865.7871 | 73577.68 | 106288.1071 | 59.09% | 61595.7871
L01560 | UKAHVRH | L01560 - NGC-240057-4 -ITK Silverstone - Define 2 / 006Ka00000NWCzsIAH # | Active | 2024-05-13 | 2025-10-31 | POC | 514150 | 452071.68 | 62078.32 | 12.07% | 490872.9465 | 403228.008 | 87644.9385 | 17.85% | -23277.0535
L01560 | UKAHXNG | L01560/NGC-240102/RPT&I Nigeria /006Ka00000NUql7IAD# | Active | 2024-10-01 | 2025-12-31 | Non POC | 0 | 18013.14 | -18013.14 | #DIV/0! | 0 | 17667.855 | -17667.855 | #DIV/0! | 0
L01560 | UKAHYAH | L01560 NGC-240128/ GPT LNG Transformation/006Ka00000NW6qLIAT# | Active | 2024-11-01 | 2025-07-31 | POC | 54463 | 43837.13 | 10625.87 | 19.51% | 33378.7229 | 26927.57 | 6451.1529 | 19.33% | -21084.2771
L01560 | UKAHYHH | L01560/ NGC-240127/RPT - Brazil Crude/006Ka00000NW6quIAD# | Active | 2024-11-25 | 2025-06-30 | POC | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0
L01560 | UKAHYPJ | L01560 - NGC-240158-1 -- TF&T - Finance Process Automation - CR 1 / 006gR0000009fyPQAQ # | Active | 2024-12-02 | 2025-12-31 | POC | 59193 | 50466.68 | 8726.32 | 14.74% | 65957.9723 | 55959.36 | 9998.6123 | 15.16% | 6764.9723
L01560 | UKAHYXI | L01560 - NGC-240160-1 -RPT UX Strategy H2 2025 / 006gR000000AdxnQAC # | Active | 2025-01-13 | 2025-12-31 | POC | 75976 | 66177.96 | 9798.04 | 12.9% | 65038.0998 | 56613.2 | 8424.8998 | 12.95% | -10937.9002
L01560 | UKAHZKP | L01560 - GPT - Brazil Nfe / 006Ka00000NWK22IAH | Active | 2025-01-01 | 2025-12-05 | POC | 110314 | 94656.06 | 15657.94 | 14.19% | 132860.3864 | 107625.375 | 25235.0114 | 18.99% | 22546.3864
L01560 | UKAHZKR | L01560/NGC-240164-2/TF&T - ARC Extension (Constellation)/0006gR0000009g4rQAA# | Active | 2025-01-02 | 2025-09-30 | POC | 59455 | 49759.48 | 9695.52 | 16.31% | 69085.3375 | 57850.88 | 11234.4575 | 16.26% | 9630.3375
L01560 | UKAHZQI | L01560/NGC-240161-1/ TF&T - E2E Process Review (Compass)/006gR000000IvXkQAK# | Active | 2025-01-20 | 2025-09-30 | POC | 45253 | 39345.32 | 5907.68 | 13.05% | 59584.1332 | 51542.4 | 8041.7332 | 13.5% | 14331.1332
L01560 | UKAHZRH | L01560/NGC-240226/L01560 - GPT SRA SAP Canada/006Ka00000NWiKcIAL# | Active | 2025-01-01 | 2025-07-31 | POC | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | #DIV/0! | 0
L01560 | UKAIANF | L01560/NGC-250012/ ST&S Silverstone - ANZ/006Ka00000QVniqIAD# | Active | 2025-04-01 | 2025-11-30 | POC | 69748 | 56443.16 | 13304.84 | 19.08% | 72317.8382 | 58451.85 | 13865.9882 | 19.17% | 2569.8382
L01560 | UKAIBDZ | L01560-NGC-250014-GPTI Euro Cons Unit Migration /006Ka00000QWgUuIAL # | Active | 2025-05-01 | 2025-08-15 | Non POC | 39153.47 | 29510.8 | 9642.67 | 24.63% | 39153 | 27576.46 | 11576.54 | 29.57% | -0.47
L01560 | UKAIBWF | L01560/NGC-250019/ST&S Brazil Marine gasoi/006Ka00000QVtCzIAL# | Active | 2025-06-02 | 2026-03-27 | Non POC | 101936.25 | 15530.02 | 86406.23 | 84.76% | 101936.25 | 15530.02 | 86406.23 | 84.76% | 0
L01560 | UKAIBWY | L01560/NGC-250029/ ST&S BR Tax Reforms/006Ka00000QVtCuIAL# | Active | 2025-06-16 | 2026-02-27 | POC | 24230 | 20823.08 | 3406.92 | 14.06% | 28704.4257 | 24666.99 | 4037.4357 | 14.07% | 4474.4257
L01560 | UKAICDT | L01560 -NGC-250020- ST&S Silverstone - Europe and IDM /006gR000000JYagQAG # | Active | 2025-06-02 | 2025-12-31 | POC | 298144 | 256434.98 | 41709.02 | 13.99% | 287493.947 | 247515.76 | 39978.187 | 13.91% | -10650.053
L01560 | UKAICDX | L01560 -NGC-250025- ST&S PRI Pre Work/006Ka00000NW82rIAD# | Active | 2025-06-16 | 2025-12-31 | POC | 107101 | 100846.98 | 6254.02 | 5.839% | 98765.0988 | 102711.08 | -3945.9812 | -3.995% | -8335.9012
L01560 | UKAIBZS | L01560 - ST&S Trading Finance Derivatives Activity/006Ka00000QVkVhIAL# | Active | 2025-07-01 | 2026-12-31 | POC | 0 | 28990.91 | -28990.91 | #DIV/0! | 78214.7533 | 45007.92 | 33206.8333 | 42.46% | 78214.7533
L01560 | UKAICNK | L01560/NGC-230148-2/ RPT Cost Management Marine CR/006Ka00000QWBagIAH# | Active | 2025-08-01 | 2026-01-31 | POC | 0 | 23225.35 | -23225.35 | #DIV/0! | 29148.2639 | 24952.23 | 4196.0339 | 14.4% | 29148.2639
STS Target | 4350000
L01560 | 3299909.4106
L01565 | 929997.1325
Total | 4229906.5431
Diff | -120093.4569

## Contractor
Contract # | Project | Account ID | Contractor Name | Third Party | Start date | End date | Cost rate/Hr | Cost Dec | Cost Jan | Cost Feb | Cost Mar | Cost Apr | Cost May | Cost Jun | Cost Jul | Source | Remarks
L01560 | Derivatives | UKAIBZS/C.26GBL.020 | Ricardo Luján | Bluetab |  |  | 66.7667 | 2675.8 |  |  | 4839.6 | 10682.672 | 9595.92 |  |  | Ledger
L01560 | Silverstone | UKAIBZS/C.26GBL.020 | Carlos Belver | Bluetab |  |  | 66.7667 | 10754.66 |  |  | 19053.13 | 8303.3496 | 10129.02 |  |  | Ledger
L01560 | Silverstone | UKAICDT/C.26GBL.021 | David Lago | Bluetab |  |  | 66.7667 | 27898.67 |  |  |  | 9613.88 | 10662.13 |  |  | Ledger
L01560 | Golden Phoenix | UKAICRW | Jose Luis Pamurega | Bluetab |  |  | 97 | [5 empty] | 9461.34 |  |  | Ledger
Big Silvestone | Silverstone | C.26K1J.001 | Daniel F Lopez | Bluetab | 2026-05-01
L01560 | Endur Settlement | UKAIEWP | Serhat | Aligne

## Sheet1
STS | 4215198.774 | 3975432.622 | 239766.152 | 5.688% | With AM
STS | 4215198.774 | 3554869.417 | 660329.357 | 15.67% | Without AM

## Signings (hidden)
| Q2 Revenue deals |  |  | M-PoC | 348750.15 |  |  |  |  | Cost Estimation in GBP
Call Upside | ISC Opportunity | Opportunity Name | Close Date | MS/M-POC | Q2 ISC Rev Est | Start Date | End Date | Plan Rev | Plan cGP% | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Remarks | Remarks 2
Pipeline | 006Ka00000QVkVhIAL | L01560 - TF Project Constellation | 2025-05-20 |  | 232500.1 | 2025-04-01 | 2025-12-31 | 750000 | [11 empty] | Solution not done
Call | 006Ka00000QVtCzIAL | L01560 - ST&S Brazil Marine gasoil | 2025-05-20 |  | 116250.05 |  |  | 432000 | [11 empty] | Solution not done